## Sheet1
TASK | OBJECTIVE | 2016-11-03 | 2016-11-07 | 2016-11-09 | 2016-11-12 | 2016-11-14 | 2016-11-16 | 2016-11-20 | 2016-11-25 | 2016-11-30 | 2016-12-01 | 2016-12-02 | 2016-12-03 | 2016-12-04
Project Specification Document | Understanding the scope of Project Specification Document | bar: 2016-11-03
Create Roles and Privileges | Creation of necessary Roles and Privileges for USERS, SYSDBA and IT Manager | bar: 2016-11-07
XOR Encryption | To devise a secret message using XOR Encryption | bar: 2016-11-09 to 2016-11-12
Network Policy Document | To prepare of Network Policy Report which complete details of company infrastructure and security policies | bar: 2016-11-12 to 2016-11-20
Physical Security Diagram | To design a complete building structure with physical ammenities | bar: 2016-12-03
Risk Assement Report | To devise a risk assessment spreadsheet that contains a list of all possible Risks factors , Probability, Impact and Effects | bar: 2016-11-12 to 2016-11-16; 2016-12-01 to 2016-12-02
Incidence Response | To prepare a incidence plan which supplies as a templete measure document when a data breech occurs | bar: 2016-11-25 to 2016-12-01
Evaluation of Usage of NoSQL | Evaluate metrics and Importance of NoSQL usage in KLJ Corporation | bar: 2016-12-01 to 2016-12-03
Conclusion | To devise a document concluding results of security measures and assessment directed to client | bar: 2016-12-04