## Sheet1
Column1 | Column2 | Column3 | Column4 | Column5 | Column6
S.No | Risk Factor | Probability "P" | Impact "I" | Risk level R=P*I | Effect
KEY
1 | Acquisition of items critical to project success could be delayed in the procurement process. | 4 | 7 | 28 | Delay in procuring could result in extension and excess overheads | 10 - Highly Critical
2 | Project schedule will exceed one fiscal year. | 5 | 6 | 30 | If delayed, the funding may go up | 1 - Low Critical
3 | Burden rates, support costs, or other charges will increase from year to year. | 5 | 8 | 40 | The contractor may neglect the work
4 | Project team member(s) will not be in place when required | 4 | 10 | 40 | Not having the required people in place to complete the project
5 | Risks associated with using off-the-shelf packages. | 8 | 8 | 64 | Their packages may not meet the need as delivered. This could potentially cause problems later if not evaluated correctly to see if all requirements are met.
6 | Risks associated with any conversions of existing data required before implementation of a new system. | 8 | 9 | 72 | If previous data from an old system is required to run a new system, data conversion will need to be closely managed to ensure it happens successfully.
7 | Risks with the hardware and software chosen to perform project development. | 7 | 10 | 70 | If the hardware and software products are prone to bugs and are “slow”, they may be inappropriate for developing a system. This can affect development, especially during the coding and testing stages.
8 | Chance that the workstation environment of the intended user will change after requirements are gathered. | 5 | 7 | 35 | There is a good chance that changes to the user's intended environment will occur, and that they will have an effect on the project.
9 | Risks to the project caused by requirements that are inadequately defined. | 7 | 7 | 49 | Requirements that are incomplete, ambiguous, or untestable will cause problems at some point during the life of the project, normally toward the end.
10 | Chance that changes, in critical personnel on either the government or contractor side, will occur during the life of the project. | 5 | 5 | 25 | If the organization historically has a high turnover rate, it can have an effect on the project and should be taken into account when planning. Any project that is planned not expecting attrition will experience an impact to the planned schedule when someone leaves.
11 | Risk to the project of a facility move during the project. | 4 | 8 | 32 | Any move of all or a part of an organization will incur a risk because it will take time away from the project.
12 | Risks associated with personnel assigned to the project who may be pulled off anytime for another assignment | 4 | 2 | 8 | Unless planned, pulling someone from the project will have an effect on the schedule of the project because that person is not available to do the work assigned to them. If done continually, it will affect the continuity of the development team.
13 | Risk to cost and schedule involved with the use of subcontractors as a part of the development effort | 4 | 5 | 20 | Subcontractor's cost schedule may be different than for an FTE and can have an effect on the cost of a project. There is a greater possibility of schedule problems with staff the project manager does not have direct control over
14 | Chance that system owner or user support staff required to be available to the development team during the software development cycle will not be available | 4 | 3 | 12 | When client support staff persons are not available to discuss the status of projects or resolve issues, it can affect everything from requirements gathering to testing. Unless someone of equal skills is made available, the schedule and quality of the product will inevitably suffer.
15 | Risk caused by a system owner's or user's representative not participating in the change control process used to manage all proposed changes to the software product from the Requirements Definition Stage forward? | 5 | 7 | 35 | Change control and configuration management are activities that are key to delivering a project on time and within budget. If there is no control of changes to requirements, design, etc., there is the potential for serious cost overruns, depending on the size of the project
16 | Risk to the project resulting from a mandated/mandatory completion date for the project. | 5 | 5 | 25 | A client directed completion simply means one of the variables that a project manager has to work with has been fixed.